## Project Planner
NSW Traffic Penalty Data Search Gantt Chart
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
[7 empty] | July | August | [22 empty] | September | [20 empty] | October
[7 empty] | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6
ACTIVITY ID | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | July 31: Week 1; August 7: Week 2; August 14: Week 3; August 21: Week 4; August 28: Week 5; September 4: Week 6; September 11: Week 7; September 18: Week 8; September 25: Week 9; October 2: Week 10
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
| Overall Project | 1 | 40 | 9 |  | 0%
1 | Project Management | 1 | 5 | 9 | 16 | 100%
1.1 | Background and Scoping | 1 | 1 | 13 | 12 | 100%
1.2 | Work Breakdown Structure | 2 | 1 | 13 | 12 | 100%
1.3 | Activity Definition | 3 | 1 | 24 | 1 | 100%
1.4 | Estimation | 4 | 1 | 24 | 1 | 100%
1.5 | Gantt Chart | 5 | 1 | 24 | 1 | 100%
2 | Software Design | 6 | 10 |  |  | 0%
2.1 | System Vision | 6 | 1 |  |  | 0%
2.2 | Requirements | 7 | 2 |  |  | 0%
2.3 | User Interface Design | 9 | 3 |  |  | 0%
2.4 | Component Design | 12 | 4 |  |  | 0%
3 | Data Analysis | 16 | 10 |  |  | 0%
3.1 | Analysis Tasks | 16 | 10 |  |  | 0%
3.2.0 | Visualisation | 26 | 5 |  |  | 0%
3.2.1 | User Interface implementation | 26 | 3 |  |  | 0%
3.2.2 | User Manual | 29 | 1 |  |  | 0%
3.2.3 | Executive Summary | 30 | 1 |  |  | 0%
3.3.0 | Testing | 31 | 10 |  |  | 0%
3.3.1 | Unit Tests | 31 | 4 |  |  | 0%
3.3.2 | Acceptance Tests | 35 | 4 |  |  | 0%
3.3.3 | Unit Test Documentation | 39 | 1 |  |  | 0%
3.3.4 | Acceptance Testing Documentation | 39 | 1 |  |  | 0%
3.3.5 | Coverage Report | 40 | 1 |  |  | 0%